## Sheet1
Updated on:2018,December,3 rd
Testing Schedule
Schedule of Final Assembly | Process | November | [16 empty] | December
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Assembly | November 17: 8; November 18: 8
Final Assembly of Inverter (First 8 Sets container) | Test | November 23: 1; November 27: 2; November 28: 1; November 29: 6; November 30: 6; December 1: 2
| Assembly | November 19: 8; November 20: 8; November 21: 8; November 22: 8; November 23: 8; November 24: 8; November 25: 8; November 26: 4
Final Assembly of Inverter (Second 30 Sets container) | Test | December 1: 6; December 2: 8; December 3: 2; December 4: 5; December 5: 2; December 6: 4; December 7: 2; December 8: 4; December 9: 2; December 10: 6; December 11: 8; December 12: 8; December 13: 1
| Assembly | November 26: 4; November 27: 8; November 28: 8; November 29: 8; November 30: 8; December 1: 8; December 2: 8; December 3: 6
Final Assembly of Inverter (Third 29 Sets container) | Test | December 13: 7; December 14: 8; December 15: 8; December 16: 8; December 17: 8; December 18: 8; December 19: 5; December 20: 2; December 21: 0; December 22: 2; December 23: 0; December 24: 2
Note:
We make adjustment according to arrange 5 stes 3.125MW heat run testing.
12-3~12-5 prepare testing bench for handling 8 hrs full load heat run test on 3125MW inverter.
12-6~12-9 two 3.125MW testing and heat run. Once the test bench ready,not need to prepare/change again, but the container wiring connect and disconnect need times( continue test 3.125 will no save time either) , so we schedule the other 3 units 3.125MW inverters testing last.
Now we are carrying out as planned, we may will make small adjustment according to the actual stituation and let you know timely.
+ one 3.125MW (2 inverter)
Two units 1.65MW inverter + one 3.125MW (2 units 1.65MW)
one 3.125MW (2 units 1.65MW)
one 3.125MW (2 units 1.65MW)
one 3.125MW (2 units 1.65MW)
Two units 1.65MW inverter + one 3.125MW (2 units 1.65MW)